## Sheet1
Milestone Name | Description | ETA | Targets | Estimated Time | Time Taken | Status | Date completed | Bugs found/ suggestions | Bugs fixed | Less priority things to work on
First | Able to demonstrate working prototype with a 5 minute call | 2021-06-21 | Search for similar open source projects and related modules that can be used | 2 days | 2 days | TRUE | 2021-06-16
|  |  | Deciding the modules that will be used and start exploring how to meet the minimum criteria. | 2 days | 2 days | TRUE | 2021-06-18
|  |  | Make a prototype using the open source projects and libraries | 1 day | 1 day | TRUE | 2021-06-19
|  |  | Finding the basic bugs in the prototype and trying to fix them | 1 day | 1 day | TRUE | 2021-06-20 | Two users are not visible on the screen; only self video | TRUE
|  |  | exploring github and Heroku and deploying the prototype | 1 day | 1 day | TRUE | 2021-06-21 | The video was not getting removed if the person leaves. | TRUE
Second | Providing video and stream related functionalities and frontend | 2021-06-28 | Setting rooms, Mute Audio & Stop video functions | 1 day | 0.5 day | TRUE | 2021-06-22
|  |  | Basic frontend for video chat window | 1 day | 1 day | TRUE | 2021-06-23
|  |  | Desging the login and register | 1 day | 1 day | TRUE | 2021-06-24
|  |  | Adding butons to the frontend part | 1 day | 0.5 day | TRUE | 2021-06-24
|  |  | Frontend for chat box | 1 day | 0.5 day | TRUE | 2021-06-25
|  |  | Integrating the frontend of video chat with backend of prototype | 1 day | 1 day | TRUE | 2021-06-26
|  |  | Figure which databases to use | 1 day | 1 day | TRUE | 2021-06-27
Third | Ablility to register new participants and have a video call b/w them Desktop: Participant will be prompted for a installation Web: Participants can start a call once they login In addition, Error Handling/Corner Case handling 1. Internet not available/going down 2. User logged in multiple times Brain-storm for more feature enrichment targeted to score higher | 2021-07-05 | Functionality of login page and register page, | 1 day | 1 day | TRUE | 2021-06-28 |  |  | login authentication............dual level verification........OTP
|  |  | Working on share link functionality | 1 day | 1 day | TRUE | 2021-06-29 | Access control: whoever created only has the access and can delete | FALSE | Forget password
|  |  | Working on leave meet button functionality | 1 day | 1 day | TRUE | 2021-06-30 | Redirection issue.....for non logged in user | TRUE | Redirection issue.....for non logged in user optimisation
|  |  | Working on chat box functionality | 2 days | 1.5 days | TRUE | 2021-07-02 | uploads folder and uploads path clash | TRUE
|  |  | Working on share screen functionality | 1 day | 0.5 day | TRUE | 2021-07-02 |  |  | Only one either display or user media
|  |  | Working on record functionality | 0.5 day | 1 day | TRUE | 2021-07-03 | Seperate screen and not proper
|  |  | Preparing documentation and testing | 1 day | 1 day | TRUE | 2021-07-04
| "Adapt Step: Incubate, design and incorporate the new feature/requirement. Any spill overs."Polishing application More corner case handling (Opportunistic) Video Recording and preparation for final submission |  | Adapt feature, chat app store in mongo | 1 day | 1 day | TRUE | 2021-07-06
Fourth |  | 2021-07-12 | Making the chat feature work without actually streaming your video and audio | 1 day | 2 day | TRUE | 2021-07-08
|  |  | Scripting for video | 1 day | 1 day | TRUE | 2021-07-09
|  |  | Record the video | 2 days | 3 days | TRUE | 2021-07-12